## Checklist
User acceptance testing checklist for a website
From https://signalcrawler.com/checklists/uat-website
# | Area | Check | How to check | Status | Notes
1 | Prepare | The requirements or user stories being accepted are listed | one row per requirement | To do
2 | Prepare | Acceptance criteria are written for each | what “done” looks like | To do
3 | Prepare | A staging site with realistic content and data is ready | not lorem ipsum | To do
4 | Prepare | Testers have accounts for each role | customer, editor, admin | To do
5 | Prepare | There is one place to record issues | a shared bug tracker with status | To do
6 | Prepare | What blocks sign-off is agreed in advance | for example, no open critical or high bugs | To do
7 | Key user journeys | A new visitor understands what the site offers from the homepage | ask someone who has not seen it | To do
8 | Key user journeys | The main goal can be completed end to end | buy, book, sign up or contact | To do
9 | Key user journeys | A visitor can find a specific product, article or service | through menu and search | To do
10 | Key user journeys | Forms collect the right data and send it where the business needs it | check the receiving end | To do
11 | Key user journeys | Confirmation messages and e-mails say the right thing | wording and details | To do
12 | Key user journeys | Logged-in users can manage their account and data | edit, delete, log out | To do
13 | Content and brand | Texts are final, correct and approved | legal and product details checked | To do
14 | Content and brand | Prices, contact details and opening hours are correct | compare with the source | To do
15 | Content and brand | Images and brand elements are approved | logos, colours, photos | To do
16 | Content and brand | Legal pages are approved by whoever is responsible | privacy, terms, cookies | To do
17 | Devices and access | Key journeys work on the phones your customers use | iPhone and Android | To do
18 | Devices and access | Key journeys work in the browsers your customers use | check analytics for the list | To do
19 | Devices and access | The site can be used with the keyboard and a screen reader for key journeys | basic check | To do
20 | Admin and data | Editors can update the content they are responsible for | without a developer | To do
21 | Admin and data | Orders, leads or bookings reach the systems that process them | CRM, e-mail, accounting | To do
22 | Admin and data | Reports and notifications reach the right people | test each one | To do
23 | Sign-off | All critical and high issues are fixed and retested | by the person who reported them | To do
24 | Sign-off | Remaining issues are accepted with a fix date | listed in the tracker | To do
25 | Sign-off | Sign-off is recorded with date, version and names | before launch | To do