## Checklist
Website launch checklist
From https://signalcrawler.com/checklists/website-launch
# | Area | Check | How to check | Status | Notes
1 | Before launch | Content is final and proofread on every page | no placeholder text, test products or dummy prices | To do
2 | Before launch | All pages work on phones at 320 to 430 px | no horizontal scroll, menus and forms usable | To do
3 | Before launch | Forms send to the right inboxes and systems | submit each one and check where it arrives | To do
4 | Before launch | Transactional e-mails come from the real domain and reach the inbox | sign-up, order, password reset | To do
5 | Before launch | Payment works in live mode with a small real purchase | then refund it | To do
6 | Before launch | Legal pages are published | privacy policy, terms, cookie notice, imprint where required | To do
7 | Before launch | The cookie banner works and trackers wait for consent where required | check the network tab before clicking | To do
8 | Before launch | Favicon, social preview image and page titles are set | share a page in a messenger to see the preview | To do
9 | Before launch | A custom 404 page answers with status 404 | try a made-up address | To do
10 | Before launch | Speed is acceptable on a mobile test | Largest Contentful Paint under 2.5 s on key pages | To do
11 | Before launch | Accessibility basics pass | keyboard use, visible focus, contrast, alt text, form labels | To do
12 | Before launch | A redirect map exists for every old URL that changes | if this replaces an old site | To do
13 | Before launch | A full backup and a rollback plan are ready | and someone knows how to use them | To do
14 | Launch day | The staging noindex is removed | check meta robots and X-Robots-Tag on several pages | To do
15 | Launch day | robots.txt allows crawling and lists the sitemap | no Disallow: / left from staging | To do
16 | Launch day | HTTP and www variants redirect with 301 to one HTTPS address | test all four | To do
17 | Launch day | The SSL certificate is valid and renews automatically | check the expiry date | To do
18 | Launch day | Old URLs redirect to their new pages in one hop | test a sample from the redirect map | To do
19 | Launch day | Canonical tags use the live domain, not staging | view source | To do
20 | Launch day | Internal links and images do not point to the staging domain | search the HTML for the staging host | To do
21 | Launch day | Analytics and tag manager fire on the live domain | check real-time reports | To do
22 | Launch day | Search Console and Bing Webmaster Tools are verified for the live domain | and the sitemap is submitted | To do
23 | Launch day | Password protection and IP restrictions are off | open the site from a phone on mobile data | To do
24 | Launch day | Caching and CDN are on, and cleared after the final deploy | check response headers | To do
25 | First week | Search Console shows pages being indexed and no spike of errors | Pages and Crawl stats reports | To do
26 | First week | A full crawl finds no broken links, redirect chains or stray noindex | run an audit on the live site | To do
27 | First week | Forms and checkout received real submissions | confirm with the people who receive them | To do
28 | First week | Server error rate and response times are normal | hosting monitoring | To do
29 | First week | Uptime monitoring and alerts are set up | someone gets notified at night | To do
30 | First week | Analytics shows traffic from all expected sources | compare with the old site if any | To do