## Checklist
Website migration checklist: keep your rankings when you move
From https://signalcrawler.com/checklists/website-migration
# | Area | Check | How to check | Status | Notes
1 | Before: record the starting point | Crawl the old site and save the full list of URLs | every indexable page, with title and H1 | To do
2 | Before: record the starting point | Export the pages with search traffic from Search Console | last 12 months, by page | To do
3 | Before: record the starting point | Export pages with backlinks | from a backlink tool, if you have one | To do
4 | Before: record the starting point | Record rankings and traffic for key pages | your baseline | To do
5 | Before: record the starting point | Save the old robots.txt, sitemap and structured data | for comparison | To do
6 | Before: plan | Every old URL with traffic or links has a new destination | in a redirect map | To do
7 | Before: plan | Redirects go to the most relevant new page, not the homepage | page to page | To do
8 | Before: plan | Content on key pages survives the redesign | compare text, headings and internal links | To do
9 | Before: plan | Titles, descriptions and H1s are carried over or improved on purpose | not reset to defaults | To do
10 | Before: plan | Structured data, hreflang and canonicals are rebuilt on the new templates | check on staging | To do
11 | Before: plan | The staging site is blocked from indexing | password or noindex, removed at launch | To do
12 | Launch | Redirects are live and return 301 in one hop | test the full redirect map, not a sample | To do
13 | Launch | The new site is indexable | no leftover noindex, robots.txt allows crawling | To do
14 | Launch | Canonicals and internal links use the new URLs | no links to old URLs or staging | To do
15 | Launch | The new sitemap lists only new, indexable URLs | submitted in Search Console | To do
16 | Launch | For a domain change, the old domain is verified and Change of Address is submitted | Search Console settings | To do
17 | Launch | Analytics and tag manager work on the new site | real-time reports | To do
18 | Launch | The old site's server keeps serving redirects | do not shut it down | To do
19 | After: the first weeks | Crawl the new site: no broken links, chains or stray noindex | full crawl | To do
20 | After: the first weeks | Search Console: watch Pages, 404s and Crawl stats daily for two weeks | new reasons appearing | To do
21 | After: the first weeks | Compare traffic per key page with the baseline | investigate pages that dropped | To do
22 | After: the first weeks | Old URLs in Search Console show “Page with redirect” | expected | To do
23 | After: the first weeks | Update external links you control | social profiles, directories, partners | To do
24 | After: the first weeks | Keep redirects in place for at least a year | longer for pages with links | To do